## Sheet1
Task | PIC | Bobot | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
DEVELOPMENT FUND
[Ureq] User Requirement |  | 10
[Document] Create FSD
[Budget Integration] Enhancement budget detail a. [new data] "txtBudgetType" (Budget QP, Development Fund) b. [new column] txtSubDistID c. Setup hierarchy budget (result endpoint)
[Maven - DF] Master ¦ Mapping SubDist a. Parent vs Child b. Parent vs Activity | CSD - RAS | 10
[Maven - DF] Master ¦ Vendor (ini kepakai saat klaim) a. ada flag apakah klaim lngsung ke KNUSER dan SUBDIST | CSD - RAS Input SND - ABM dpt notif
[Maven - DF] Transaction ¦ Memo QP (Create and Close) | CCD | 10
[Maven - DF] Transaction ¦ Inject Development Fund (Data Uniq by Memo QP) a. [Trial] automate get file from "aries.enseval.com" b. Result into Budget Integration Budget Type = Development Fund SubDist = Spesific SubDist depends file EPM (from ETPM template) Level Budget = Glondongan (Z01) c. Report Monitoring per SubDist d. Mekanisme SubDist Resign (Reclass Budget) | System | 10
[Kicao-KDS] Transaction ¦ MKPP a. Create base on Budget Type "Development Fund" (per subdist, per activity, with nominal) (strict budget) b. Picklist MKPP base on Memo QP (Spesific) (ini ga perlu) | CCD
[Kicao-KDS] Transaction ¦ KLAIM a. [Kicao-KDS] Create Klaim (add information MKPP) (boleh budget minus, ada notif) (infomasi kan saldo sisa df dan memo) b. [PRM] Create Klaim (add information MKPP) (boleh budget minus, ada notif) (infomasi kan saldo sisa df dan memo) c. ada tambahan 0.5% (config) dari tagihan yang diinput (angka dpp) | Admin HO Admin Subdist CF (validate & app)
[Kicao-KDS] Transaction ¦ KLAIM MATCHING a. Handling Condition, jika transaksi ini untuk DF tidak akan push ke oracle dan hanya memotong saldo DF nya saja di BI | System (auto matching) | 20
SIT
UAT |  | 10
GO LIVE |  | 10 | bar: 2026-09-01 W1
Note on A12: Jika ini bisa diprovide untuk Admin SubDist kasi tau klaim ini untuk MKPP yang mana, sistem akan bisa melakukan auto matching untuk pemotongan DF saat dokumen sudah di validasi